## RFI Log
RFI No. | Title | Question summary | Raised by | Assigned to | Date raised | Response due | Date answered | Status | Impact (cost/schedule/none) | Linked documents | Notes
RFI-001 | Level 2 slab edge detail | Level 2 slab edge detail conflicts with facade bracket layout; confirm which detail governs | J. Carter (Site Manager) | Architect | 2026-07-06 | 2026-07-13 | 2026-07-10 | Closed | None | A-201 Rev C; S-105 Rev B | Structural detail governs; facade brackets adjusted
RFI-002 | Substation ductbank routing | Electrical ductbank route clashes with storm drain shown on civil plans; propose 600mm offset south | M. Osei (Project Engineer) | Civil Engineer | 2026-07-09 | 2026-07-16 |  | Open | Schedule | C-301 Rev A; E-110 Rev B | Reminder sent; duct delivery held pending answer
RFI-003 | Door hardware finish | Spec section 08 71 00 lists two finishes for ground floor doors; confirm which applies | L. Novak (Package Manager) | Architect | 2026-07-12 | 2026-07-19 | 2026-07-15 | Answered | Cost | Spec 08 71 00; A-601 Rev B | Satin finish confirmed; pricing being checked before close-out
RFI-004
RFI-005
RFI-006
RFI-007
RFI-008
RFI-009
RFI-010
RFI-011
RFI-012
RFI-013