## Template
Item No. | Description of work | Scheduled value | Work completed previous periods | Work completed this period | Materials presently stored | Total completed and stored to date | % complete | Balance to finish | Retainage
01 | Site preparation and groundworks | 120000 | 96000 | 24000 | 0 | 120000 | 100% | 0 | 6000
02 | Concrete frame | 340000 | 170000 | 68000 | 12000 | 250000 | 74% | 90000 | 12500
03 | Mechanical and electrical first fix | 210000 | 42000 | 31500 | 8000 | 81500 | 39% | 128500 | 4075